## Sheet1
SMART METER DESIGN PROJECT
TASK | START | TARGET FINISH |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7
|  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Team Roles | 2023-01-30 | 2023-02-02 | 100%
Box Design | 2023-01-30 | 2023-02-07 | 100%
PSU Design | 2023-01-30 | 2023-02-08 | 100%
PSU Testing | 2023-02-09 | 2023-02-22 | 70%
Presentation | 2023-02-09 | 2023-02-13 | 100%
Order | 2023-02-07 | 2023-02-13 | 100%
Interface Circuitry | 2023-02-09 | 2023-02-22 | 60%
Interface Testing | 2023-02-23 | 2023-03-12
Software Design | 2023-02-09 | 2023-02-22
Software Testing | 2023-02-23 | 2023-03-12
Box Construction | 2023-02-07 | 2023-02-26
Integration | 2023-02-27 | 2023-03-12
Quality Check | 2023-03-06 | 2023-03-15
Overall Testing | 2023-03-06 | 2023-03-17
Group Report | 2023-03-06 | 2023-03-17